## Mehtab
To-do list
To be completed by: |  | 2025-05-18 |  | Name - Mehtab - Group Leader
Deadline: |  | 2025-05-18 |  | Date - 5/18/2025
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Specifics + Revision Notes
100% | Planning | 2025-04-24 | 2025-04-30 | 2025-05-02 | 8 days | Numerous meetings to understand the specifics of the project and what to do
100% | Preparation | 2025-05-03 | 2025-05-05 | 2025-05-05 | 2 days | Meetings to divide the work appropriateley
100% | Database creation logic | 2025-05-07 | 2025-05-07 | 2025-05-07 | 1 days | PrestigeCars_3NF
100% | Schema creation | 2025-05-08 | 2025-05-08 | 2025-05-09 | 2 days | Data, Reference, DataTransfer, SourceData, Output, Project2.5, Process
100% | Table definitions | 2025-05-10 | 2025-05-14 | 2025-05-14 | 4 days | ALL CREATE TABLE statements across all schemas + Reference.MarketingInformation, SourceData.SalesText
100% | Cleaning logic across all schemas + scripts | 2025-05-15 | 2025-05-17 | 2025-05-17 | 2 days | Managed all data insert-cleaning scripts
100% | Video | 2025-05-18 | 2025-05-18 | 2025-05-18 | 1 days | Record
100% | Hand-off | 2025-05-18 | 2025-05-18 | 2025-05-18 | 1 days | Follow up and made sure all work is done
100% | Follow-up | 2025-05-18 | 2025-05-18 | 2025-05-18 | 1 days | Follow up and made sure all work is done

## Ashley
To-do list
To be completed by: |  | 2025-05-18 |  | Name - Ashley - Co-leader
Deadline: |  | 2025-05-18 |  | Date - 5/18/2025
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Specifics + Revision Notes
100% | Planning | 2025-04-24 | 2025-04-30 | 2025-05-02 | 8 days | Numerous meetings to understand the specifics of the project and what to do
100% | Split up Work / Preperation | 2025-05-03 | 2025-05-05 | 2025-05-05 | 2 days | Meetings to divide the work appropriateley
100% | Schema design | 2025-05-07 | 2025-05-07 | 2025-05-07 | 1 days | ALL SCHEMAS
100% | UDT Design | 2025-05-08 | 2025-05-08 | 2025-05-09 | 2 days | ALL UDTS
100% | Normalization and FK Validity | 2025-05-10 | 2025-05-14 | 2025-05-14 | 4 days | Data Validation Queries, Row count comparison, Foreign key integrity checks (Sales to Customer, etc.)
100% | More table defiinitions | 2025-05-15 | 2025-05-17 | 2025-05-17 | 2 days | Reference.Country, Data.Customer, Data.Sales
100% | Documentation and team communication | 2025-05-18 | 2025-05-18 | 2025-05-18 | 1 days | Lead compiling of ALL DOCUMENTATION
100% | Video | 2025-05-18 | 2025-05-18 | 2025-05-18 | 1 days | Record
100% | Follow-up | 2025-05-18 | 2025-05-18 | 2025-05-18 | 1 days | Follow up and made sure all work is done
100% | Hand-off | 2025-05-18 | 2025-05-18 | 2025-05-18 | 1 days | Follow up and made sure all work is done

## William
To-do list
To be completed by: |  | 2025-05-18 |  | Name - William
Deadline: |  | 2025-05-18 |  | Date - 5/18/2025
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Specifics + Revision Notes
100% | Planning | 2025-04-24 | 2025-04-30 | 2025-05-02 | 8 days | Numerous meetings to understand the specifics of the project and what to do
100% | Preparation | 2025-05-03 | 2025-05-05 | 2025-05-05 | 2 days | Meetings to divide the work appropriateley
100% | Views | 2025-05-07 | 2025-05-07 | 2025-05-07 | 1 days | vw_SalesCategory, vw_Staff, vw_StaffHierarchy, vw_YearlySales, vw_SalesInPounds, vw_SalesText
100% | Inline Table-Valued Functions | 2025-05-08 | 2025-05-08 | 2025-05-09 | 2 days | fn_GetAllSales, fn_StockPricesByMake, fn_BudgetByYearMonth
100% | Table work | 2025-05-10 | 2025-05-14 | 2025-05-14 | 4 days | Reference.YearlySales, SourceData.SalesInPounds. Output.StockPrices
100% | Presentation | 2025-05-15 | 2025-05-17 | 2025-05-17 | 2 days | COMPILED ALL WORK INTO SLIDES
100% | Video | 2025-05-18 | 2025-05-18 | 2025-05-18 | 1 days | Record
100% | Hand-off | 2025-05-18 | 2025-05-18 | 2025-05-18 | 1 days | Follow up and made sure all work is done
100% | Follow-up | 2025-05-18 | 2025-05-18 | 2025-05-18 | 1 days | Follow up and made sure all work is done

## Maitri
To-do list
To be completed by: |  | 2025-05-18 |  | Name - Maitri
Deadline: |  | 2025-05-18 |  | Date - 5/18/2025
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Specifics + Revision Notes
100% | Planning | 2025-04-24 | 2025-04-30 | 2025-05-02 | 8 days | Numerous meetings to understand the specifics of the project and what to do
100% | Preparation | 2025-05-03 | 2025-05-05 | 2025-05-05 | 2 days | Meetings to divide the work appropriateley
100% | Reference schemas | 2025-05-07 | 2025-05-07 | 2025-05-07 | 1 days | ALL SCHEMAS
100% | Lookup tables | 2025-05-08 | 2025-05-08 | 2025-05-09 | 2 days | Reference.Country, Reference.Color, Reference.Budget, Reference.SalesCategory, Reference.Staff, Reference.StaffHierarchy
100% | Normalizing | 2025-05-10 | 2025-05-14 | 2025-05-14 | 4 days | Contributed to planning normalized foreign key mapping (CountryID, ColorID, etc.)
100% | Validation | 2025-05-15 | 2025-05-17 | 2025-05-17 | 2 days | Made sure everything can run
100% | Video | 2025-05-18 | 2025-05-18 | 2025-05-18 | 1 days | Record
100% | Hand-off | 2025-05-18 | 2025-05-18 | 2025-05-18 | 1 days | Follow up and made sure all work is done
100% | Follow-up | 2025-05-18 | 2025-05-18 | 2025-05-18 | 1 days | Follow up and made sure all work is done

## Nayem
To-do list
To be completed by: |  | 2025-05-18 |  | Name - Nayem
Deadline: |  | 2025-05-18 |  | Date - 5/18/2025
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Specifics + Revision Notes
100% | Planning | 2025-04-24 | 2025-04-30 | 2025-05-02 | 8 days | Numerous meetings to understand the specifics of the project and what to do
100% | Preparation | 2025-05-03 | 2025-05-05 | 2025-05-05 | 2 days | Meetings to divide the work appropriateley
100% | Utility stored procedures | 2025-05-07 | 2025-05-07 | 2025-05-07 | 1 days | TruncateStarSchemaData, DropForeignKeysFromStarSchema
100% | Created stub for logging procedure | 2025-05-08 | 2025-05-08 | 2025-05-09 | 2 days | DataTrackWorkFlow
100% | Data migration scripts | 2025-05-10 | 2025-05-14 | 2025-05-14 | 4 days | Data.Sales, Data.SalesDetails, Data.Customer
100% | Gantt/TDL | 2025-05-15 | 2025-05-17 | 2025-05-17 | 2 days | Work on all GANTT/TDL documentation
100% | Video | 2025-05-18 | 2025-05-18 | 2025-05-18 | 1 days | Record
100% | Hand-off | 2025-05-18 | 2025-05-18 | 2025-05-18 | 1 days | Follow up and made sure all work is done
100% | Follow-up | 2025-05-18 | 2025-05-18 | 2025-05-18 | 1 days | Follow up and made sure all work is done

## Sabrina
To-do list
To be completed by: |  | 2025-05-18 |  | Name - Sabrina
Deadline: |  | 2025-05-18 |  | Date - 5/18/2025
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Specifics + Revision Notes
100% | Planning | 2025-04-24 | 2025-04-30 | 2025-05-02 | 8 days | Numerous meetings to understand the specifics of the project and what to do
100% | Preparation | 2025-05-03 | 2025-05-05 | 2025-05-05 | 2 days | Meetings to divide the work appropriateley
100% | Team Collaboration | 2025-05-07 | 2025-05-07 | 2025-05-07 | 1 days | More meetings
100% | Data validation | 2025-05-04 | 2025-05-14 | 2025-05-18 | 10 days | IN CHARGE OF CHECKING ALL CODE
100% | Video | 2025-05-18 | 2025-05-18 | 2025-05-18 | 1 days | Record
100% | Hand-off | 2025-05-18 | 2025-05-18 | 2025-05-18 | 1 days | Follow up and made sure all work is done
100% | Follow-up | 2025-05-18 | 2025-05-18 | 2025-05-18 | 1 days | Follow up and made sure all work is done